## Slide 1: Initial Planning Meeting REP Dress Rehearsal – 01/01/01 REP Evaluated Exercise – 01/01/01
As of: 01 MAR 0000

## Slide 2: Agenda
Exercise Scope
Mission Areas
Objectives/Aligned Core Capabilities
Exercise Date and Duration
Participating Organizations/Venues
Extent of Play
Exercise Planning Team
Exercise Assumptions and Artificialities
Exercise Security Organization and Structure
Exercise Control and Evaluation Structure

## Slide 3: Agenda
Exercise Resources
Exercise Logistics
Planning Timeline and Milestones
Local Issues, Concerns, and Sensitivities
SME Expertise Needed (SIMCELL)
Contingency Plan Discussion
Follow-On Meeting Dates, Times, Locations

## Slide 4: Exercise Scope
Focused on CGS 10-mile EPZ
Organizations
  (Name) Northwest
  (Name) County
  (Name) County
  WA EMD
  WA DOH
  WA AGR
  OR DOE

## Slide 5: Design and Development Resources
Mission Area (ref RPM (2016) Exhibit II-1, pp 19-20)
  Response
    Planning
    Public Information and Warning
    Operational Coordination
    Critical Transportation
    Environmental Response/Health and Safety
    Mass Care Services
    Operational Communications
    Public Health, Healthcare, and Emergency Medical Services
    Situational Assessment

## Slide 6: Proposed Criteria and Core Capabilities
1.a.1. – Operational Communications
1.b.1. – N/A
1.c.1. – Operational Coordination, Operational Communications, Situational Awareness
1.d.1. – Operational Communications
1.e.1. – Environmental Response/Health and Safety, Mass Care Services, Public and Private Services and Resources, Public Health and Medical Services
2.a.1. – Operational Coordination, Environmental Response/Health and Safety, Situational Assessment

## Slide 7: Proposed Criteria and Core Capabilities
2.b.1. – Operational Coordination, Environmental Response/Health and Safety, Operational Communications, Situational Assessment
2.b.2. – Operational Coordination, Environmental Response/Health and Safety, Operational Communications, Situational Assessment
2.c.1. – Operational Coordination, Operational Communications, Situational Assessment
3.a.1. – Operational Coordination, Environmental Response/Health and Safety

## Slide 8: Proposed Criteria and Core Capabilities
3.b.1. – Public Information and Warning, Operational Coordination, Environmental Response/Health and Safety, Public and Private Services and Resources
3.c.1. – Public Information and Warning, Operational Coordination, Critical Transportation, Environmental Response/Health and Safety
3.c.2. – Operational Coordination, Critical Transportation, Environmental Response/Health and Safety
3.d.1. – Operational Coordination, Critical Transportation, On-Scene Security and Protection
3.d.2. - Operational Coordination, Critical Transportation, Infrastructure Systems

## Slide 9: Proposed Criteria and Core Capabilities
4.a.2. – Operational Coordination, Situational Assessment
4.a.3. – N/A
5.a.1. – Public information and Warning, Operational Coordination, Operational Communications
5.a.3. – Public information and Warning, Operational Communications
5.b.1. – Public information and Warning, Operational Communications

## Slide 10: Exercise Date and Duration
Dress Rehearsal 01/01/01; Evaluated Exercise 01/01/01
Duration: 5+ hours
Participating Organizations/Venues
(Name)– EOF, MUDAC, JIC
EMD – State EOC, JIC, EOF, Counties
(Name) – EOC, JIC
(Name) – ECC, JIC
DOH – SEOC, ACC, FMT (2), MUDAC, JIC
WSDA – SEOC, ACC, JIC, Counties
OR DOE – EOC, FMT
FEMA R10 – FIT Team, IMAT, RRCC

## Slide 11: Extent of Play
Previously approved Extent of Play. Modify as needed. Include Level 2 and Planning Issue redemonstrations.
Submit to Johnson NLT 01/01/01.
Exercise Planning Team
(Organization) – Last, Last
EMD – Williams, Johnson

## Slide 12: Exercise Assumptions and Artificialities
Canned weather – Need to update 2020 temps
Weather product injects based upon venue procedures.
Field Team data/activities – in the field or parking lot?
Approved simulated activities must be documented in EOP. If player simulates action – must be documented.
No live EAS or CodeRED activations. Simulate and document.
No public info documents or social media (SM) posts/tweets to non-exercise participants. Can use email or other method to document SM posts/tweets.

## Slide 13: Exercise Control and Evaluation Structure
ERO and each ORO will have 1 Lead Controller.
Each venue/field location will have 1 Lead Venue Controller; may have additional Controllers for larger venues. Venue Controllers report to appropriate Lead Venue Controller.
Strict adherence to MSEL – no impromptu injects without Lead Controller approval.
Lead Controllers coordinate directly to resolve issues
ORO SIMCELL. Each entity to provide support. Minimum 1.
Each venue to have at least one FEMA evaluator for EE.
AAR to be done by FEMA.

## Slide 14: Exercise Security Organization and Structure
Each venue to follow own venue security protocols during DR/EE per Plan/procedures. If different, document in EOP.
All exercise documents are exercise sensitive and should be marked and handled as such. Tri-Fold brochure/EXPLAN okay to distribute
All injects and exercise documents to be marked as "Exercise".
All phone conversations to begin/end with “This is an exercise”.

## Slide 15: Exercise Resources
No FRMAC resources
Use location for SIMCELL.
Exercise Logistics
Each venue responsible for own meals
EMD to provide meals for SEOC and SIMCELL
SIMCELL to follow Multi-Purpose Facility restrictions regarding COVID

## Slide 16: Planning Timeline and Milestones
Review and adjust planning timeline document, if needed.
Local Issues, Concerns, and Sensitivities
Observer policy
  Escorted
  No contact with players
  Clearly identified (vest, badge, hat, pink feathered boa, etc.)
Anything else?

## Slide 17: SME Expertise Needed
NWS for Spot Weather Forecast
What expertise is needed on the SIMCELL? Law enforcement? Fire?
Contingency Plan Discussion
Contingency injects for critical tasks/decisions.
Possible weather concerns in October (driving over mountain passes)
Out-of-Area Players arrive in area day before

## Slide 18: Follow-On Meetings/Due Date Info
Location – Virtual (MS Teams)
EOP changes due to EMD – 01/01/01
MSELs (DR and EE) due to EMD – 01/01/01
MPM – 01/01/01
Plan/Procedures of Record due to FEMA – 01/01/01
FPM – 01/01/01
C/E Briefing (DR/EE) – 01/01/01/ 01/01/01 (AM)
SIMCELL training (DR/EE) – 01/01/01 / 01/01/01 (PM)

## Slide 19: Closing
Meeting milestones/deadlines is critical to success.
Questions/Comments?