## Slide 1: Mid-Term Planning Meeting REP Dress Rehearsal Exercise – 01/01/01 REP Evaluated Exercise – 01/01/01
As of: 01 MAY 01

## Slide 2: Agenda
Sign-In
Meeting Focus
  Exercise Organization and Staffing
  Scenario Timeline development
    Dress rehearsal
    Evaluated exercise
  Scheduling
  Logistics
  Administrative requirements
  Review draft documentation

## Slide 3: Exercise Organization and Staffing
Staffing needs to be the same for DR as well as the EE.
State agencies to provide name with staffing pattern input.
Staffing pattern will be out for input 30 days before DR and EE. Name is POC.

## Slide 4: Scenario Timelines
Review timelines
  Dress Rehearsal
  Evaluated Exercise
Radiological Data
  agency to produce.
  DOH to review
  Deadline to get to FEMA for review/approval – 01/01/01. Earlier is better.

## Slide 5: Scheduling
Upcoming Due Dates
  Extent of Play due to FEMA – 01/01/01
  Plan/Procedures of record due to FEMA – 01/01/01
    Send to name, copy name. Prefer upload to Region X PTK
  Firm up C/E Briefings for DR and EE and location.
    Coordinate with FEMA and EPT members
  Firm up SIMCELL trainings
    DR and EE
    Location Room?

## Slide 6: Logistics
SIMCELL
  Need name(s) and contact info from each jurisdiction.
  SIMCELL training to be held 1 day before DR/EE.
    Will schedule specific dates once we have names and contact info.
  Will provide lunches.
  Willing to consider travel expenses if using someone from another county (50+ miles).

## Slide 7: Administrative
Weather injects.
  Confirm what each local venue uses.
    Spot Weather Forecast
    NWS 7-day Forecast
MSEL Meeting
  Date/location
  Do DR and EE at single meeting.

## Slide 8: Review Documentation
C/E Handbooks – DR and EE
  Communications checks (Annexes A & C)
  Scenarios updates?
  Controller info
  SIMCELL location, names, and phone numbers
  Schedule C/E Briefing.
    DR – Suggest morning before DR.
    EE – Suggest FEMA hotel conference room on morning before EE
  Controller Debrief date/location. Combine with AAC?
  Appendix D. Are the maps the correct version?

## Slide 9: Review Documentation
EOP
  Area 1
    1.a.1. County MS-1. When in 2021?
    1.c.1. County TCP/ACP.
    May need more room for this slide.

## Slide 10: Closing
Meeting milestones/deadlines is critical to success.
Questions/Comments?