## ESF and SEOC Checklists
Catastrophic Incident Annex
Appendix 2-4 Emergency Support Function and SEOC Section Checklists
Primary Core Capability | Supporting Core Capability | Phase | Primary ESF/Section | Secondary ESF/Section | Activity | CIA
Critical Transportation | Operational Coordination | 2a | Operations Section | Logistics Section | Establish contact between WSDOT HQ and the SEOC | CSZ
Critical Transportation | Operational Coordination | 2a | Operations Section | SEOC Supervisor | Determine transportation-related ICS positions needed for staffing of ESF 1 | CSZ
Critical Transportation | Operational Coordination | 2a | Operations Section | Planning Section | Receive situation reports from WSDOT HQ concerning regional conditions to include damage status and available capabilities | CSZ
Critical Transportation | Operational Coordination | 2a | ESF 1 | Planning Section | Identify routes that are being assessed and their priority/sequence of assessment | CSZ
Critical Transportation | Operational Coordination | 2a | ESF 1 | ESF 6 | Coordinate with ESF 6 for evacuation routes that will be needed | CSZ
Critical Transportation | Operational Coordination | 2a | ESF 1 |  | Identify temporary bypasses to impacted infrastructure | CSZ
Critical Transportation | Operational Coordination | 2a | UCG | SEOC Supervisor | UCG outlines response goals based on conditions, damage, and available resources on-hand | CSZ
Critical Transportation | Operational Coordination | 2a | ESF 1 | Planning Section | SEOC/ESF 1 develops response objectives based on UCG goals for: (1) Tracking deployment and status of assessment teams, repair teams, and debris clearance teams; (2) Repair priorities (to include temporary bypasses); (3) Evacuation route conditions; (4) Evacuation transportation resources; (5) Establishing access for movement of resources into affected areas | CSZ
Critical Transportation | Operational Coordination | 2a | ESF 1 | Policy Group | Coordinate with local emergency management and public works to determine if state transportation resources can be used to support the establishment of local priority routes which support objectives | CSZ
Critical Transportation | Operational Communications | 2a | ESF 2 | Logistics Section | Ensure the capability to communicate with WSDOT HQ | CSZ
Critical Transportation | Operational Communications | 2a | ESF 2 | ESF 1 | Ensure that WSDOT HQ can communicate with regional offices and other field operations | CSZ
Critical Transportation | Operational Communications | 2a | ESF 2 | Logistics Section | Establish the ability to provide communications to SSAs | CSZ
Critical Transportation | Operational Communications | 2a | ESF 2 | ESF 1 | Determine capabilities needed to support communications with private airports, maritime, and rail partners which may be used during the response | CSZ
Critical Transportation | Operational Communications | 2a | ESF 2 | Logistics Section | Ensure the capability to communicate with local and Tribal partners for transportation response | CSZ
Critical Transportation | Operational Communications | 2a | ESF 2 | Logistics Section | Ensure the capability to communicate with FEMA Region 10 | CSZ
Transportation | Logistics and Supply Chain Management | 2a | ESF 1 | ESF 3 | Determine initial resource deficiencies for debris clearance and highway/bridge assessments | CSZ
Transportation | Logistics and Supply Chain Management | 2a | Logistics Section | UCG | Push initial mission ready packages to support previously identified resource gaps | CSZ
Transportation | Logistics and Supply Chain Management | 2a | ESF 1 | ESF 3 | Determine initial capabilities needed to meet debris clearance operations and assessments | CSZ
Transportation | Logistics and Supply Chain Management | 2a | Logistics Section | Operations Section | Determine composition of EMAC and federal requests needed for debris clearance and assessment resources | CSZ
Transportation | Logistics and Supply Chain Management | 2a | Logistics Section | Planning Section | Stand-up and staff SSAs | CSZ
Transportation | Logistics and Supply Chain Management | 2a | Logistics Section | ESF 7 | Make preparations for resource coordination between SSAs, FSAs, APODs, and the ISB | CSZ
Transportation | Logistics and Supply Chain Management | 2a | Operations Section | ESF 7 | Support requests for evacuation resources | CSZ
Transportation | Situational Assessment | 2a | Planning Section | ESF 1 | Map impacted state routes (roadways and bridges) into GIS using Priority Routes layer: (1) Determine nature of impact (e.g., landslide, bridge collapse, etc.); (2) Map impacted local priority routes into GIS using Priority Routes layer | CSZ
Transportation | Situational Assessment | 2a | Planning Section | ESF 1 | Map impacted WSDOT Ferry terminals into GIS using Priority Routes layer | CSZ
Transportation | Situational Assessment | 2a | Planning Section | ESF 1 | Map impacted maritime ports into GIS using Priority Routes layer | CSZ
Transportation | Situational Assessment | 2a | Planning Section | ESF 1 | Map impacted airports into GIS using Priority Routes layer: (1) Identify airports with impacted access that are designated as SSAs, APODs, and FSAs | CSZ
Transportation | Situational Assessment | 2a | Planning Section | ESF 1 | Map impacted rail lines into GIS using Priority Routes layer | CSZ
Transportation | Situational Assessment | 2a | ESF 1 | Planning Section | Identify areas that are inaccessible or cut-off due to damaged state routes | CSZ
Transportation | Situational Assessment | 2a | ESF 1 | Planning Section | Determine impacts status of Transportation Community Lifeline | CSZ
Mass Care Services | Operational Coordination | 2a | ESF 6 | Logistics Section | Establish contact with impacted jurisdictions to identify shelters in use: (1) Identify shelter types; (2) Identify sheltering staff shortfalls; (3) Identify shelter resource deficiencies | CSZ
Mass Care Services | Operational Coordination | 2a | ESF 6 | Planning Section | Identify mass care-related ICS positions needed to staff the Human Services Branch and ESF 6 based on sheltering needs identified by local jurisdictions | CSZ
Mass Care Services | Operational Coordination | 2a | ESF 6 | SEOC Supervisor | Alert and notify all mass care response partners in accordance with procedures | CSZ
Mass Care Services | Operational Coordination | 2a | ESF 6 | Planning Section | Receive situation reports from activated ESFs participating in mass care activities concerning the condition and availability of their resources | CSZ
Mass Care Services | Operational Coordination | 2a | ESF 1 | ESF 6 | Determine the status of routes which align with Priority Routes: (1) Assess the ability of resources to access shelters and inform local jurisdictions | CSZ
Mass Care Services | Operational Coordination | 2a | ESF 8 | ESF 6 | Identify medical support capabilities for shelters | CSZ
Mass Care Services | Operational Coordination | 2a | ESF 12 | ESF 6 | Identify energy infrastructure impacts which affect sheltering operations | CSZ
Mass Care Services | Operational Coordination | 2a | ESF 15 | JIC | Assist local jurisdictions in providing or amplifying public information and warning to impacted communities | CSZ
Mass Care Services | Operational Coordination | 2a | ESF 20 | ESF 6 | In coordination with the Washington National Guard, provide personnel to support local mass care operations | CSZ
Mass Care Services | Operational Communications | 2a | ESF 2 | ESF 6 | Assess and establish communications ability with all mass care response partners | CSZ
Mass Care Services | Operational Communications | 2a | ESF 2 | ESF 6 | Assess and establish communications ability with all impacted jurisdiction’s mass care operations | CSZ
Mass Care Services | Operational Communications | 2a | ESF 2 | ESF 6 | Identify any communications barriers with state, Tribal, and local mass care operations and begin identifying solutions | CSZ
Mass Care Services | Operational Communications | 2a | ESF 15 | JIC | Monitor for community-based communications concerning mass care | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2a | Logistics Section |  | Coordinate with local emergency management logistics to identify anticipated resource shortfalls and needs | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2a | Logistics Section | ESF 7 | Assist local jurisdictions in identifying vendors for resource requests | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2a | Logistics Section | Policy Group | Compile resource needs and identify trends to provide to policy group for resource request funding | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2a | Logistics Section | ESF 7 | Identify scarce resources | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2a | Policy Group | UCG | Begin to develop prioritization methodology in coordination with UCG and policy group | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2a | ESF 7 | Logistics Section | Identify vendors in non-impacted areas who have water and shelf stable food inventories on-hand | CSZ
Mass Care Services | Situational Assessment | 2a | ESF 6 |  | Monitor WebEOC Shelter Status Dashboard | CSZ
Mass Care Services | Situational Assessment | 2a | ESF 6 | ESF 11 | Conduct ongoing assessment of mass care needs | CSZ
Mass Care Services | Situational Assessment | 2a | ESF 6 | ESF 11 | Estimate initial mass care needs by type and capability | CSZ
Mass Care Services | Situational Assessment | 2a | ESF 6 | Planning Section | Provide quantitative mass care services data to Planning and Logistics Sections, and other ESFs that require accurate data for response logistics | CSZ
Mass Care Services | Situational Assessment | 2a | ESF 6 | ESF 11 | Implement a daily counting and reporting system for sheltering, feeding, and bulk distribution items delivered | CSZ
Mass Care Services | Situational Assessment | 2a | ESF 6 | Planning Section | Identify initial conditions of the Food, Water, Shelter & Health and Medical community lifelines | CSZ
Infrastructure Systems | Operational Coordination | 2a | Operations Section |  | In coordination with the Business and Infrastructure Group, establish coordination between infrastructure partners who share dependencies with impacted systems (water systems require fuel/electricity; transportation repairs may require water; fuel refinement requires potable water) | CSZ
Infrastructure Systems | Operational Communications | 2a | ESF 15 | JIC | Ensure the capability to provide the public with timely warning and emergency information concerning water resources. | CSZ
Infrastructure Systems | Logistics and Supply Chain Management | 2a | ESF 6 | Logistics Section | Identify additional water resources available to support local resources to meet needs (bottled water, RUPUs, water trailers, etc.) | CSZ
Infrastructure Systems | Situational Assessment | 2a | ESF 6 | ESF 1 | Identify impacts to the transportation system delaying or preventing the movement of water resources. | CSZ
Infrastructure Systems | Situational Assessment | 2a | ESF 6 | ESF 5 | Identify local CPODs requiring water resources | CSZ
Critical Transportation | Operational Coordination | 2b | ESF 1 | UCG | Develop a time-based plan to restore operation of lifeline routes, or alternate routes if the lifeline routes are severely damaged, and ports of entry | CSZ
Critical Transportation | Operational Coordination | 2b | ESF 1 | ESF 3 | Coordinate assessment of debris clearance/removal and repair efforts through WSDOT regional EOCs: (1) Begin debris removal and emergency repairs necessary to reestablish transportation corridors for increased capacities | CSZ
Critical Transportation | Operational Coordination | 2b | ESF 1 |  | Determine repair requirements for maritime infrastructure: (1) Assess the viability and requirements for establishing minimal operations | CSZ
Critical Transportation | Operational Coordination | 2b | UCG | SEOC Supervisor | UCG updates response goals based on conditions, damage, and available resources on-hand | CSZ
Critical Transportation | Operational Coordination | 2b | ESF 1 | Planning Section | SEOC/ESF 1 updates response objectives based on UCG goals for: (1) Tracking deployment and status of assessment teams, repair teams, and debris clearance teams; (2) Repair priorities (to include temporary bypasses); (3) Evacuation route conditions; (4) Evacuation transportation resources; (5) Establishing access for movement of resources into affected areas | CSZ
Critical Transportation | Operational Coordination | 2b | ESF 1 | UCG | Coordinate with Federal ESF 1 on response needs | CSZ
Critical Transportation | Operational Communications | 2b | ESF 2 | Logistics Section | Sustain the capability to communicate with WSDOT HQ | CSZ
Critical Transportation | Operational Communications | 2b | ESF 2 | Logistics Section | Sustain communications between WSDOT HQ and regional offices and other field operations | CSZ
Critical Transportation | Operational Communications | 2b | ESF 2 | Logistics Section | Sustain the ability to communication with SSAs | CSZ
Critical Transportation | Operational Communications | 2b | ESF 2 | Logistics Section | Ensure the capability to communicate with Local Staging Areas | CSZ
Critical Transportation | Operational Communications | 2b | ESF 2 | Logistics Section | Sustain capabilities to support communications with private airports, maritime, and rail partners which may be used during the response | CSZ
Critical Transportation | Operational Communications | 2b | ESF 2 | Logistics Section | Sustain communications with FEMA Region 10 | CSZ
Critical Transportation | Logistics and Supply Chain Management | 2b | ESF 7 | Logistics Section | Support resource requests for transportation resources | CSZ
Critical Transportation | Logistics and Supply Chain Management | 2b | Logistics Section | ESF 7 | Identify external resources that can support response objectives | CSZ
Critical Transportation | Logistics and Supply Chain Management | 2b | Logistics Section | UCG | Track mutual aid and federal resources employed by the state | CSZ
Critical Transportation | Logistics and Supply Chain Management | 2b | Logistics Section | ESF 7 | Identify barriers for the movement of resources | CSZ
Critical Transportation | Logistics and Supply Chain Management | 2b | Logistics Section | ESF 7 | Identify alternative methods for the movement for resources | CSZ
Critical Transportation | Situational Assessment | 2b | Planning Section | ESF 1 | Maintain map of impacted state routes (roadways and bridges) in the GIS Priority Routes layer | CSZ
Critical Transportation | Situational Assessment | 2b | Operations Section | ESF 1 | Assess if available priority routes are connecting staging areas, points of distribution, points of entry, hospitals, and emergency services including police and fire. | CSZ
Critical Transportation | Situational Assessment | 2b | ESF 1 |  | Identify areas that are inaccessible or cut-off due to damaged state routes | CSZ
Critical Transportation | Situational Assessment | 2b | ESF 1 | Planning Section | Determine impacts status of Transportation Community Lifeline: (1) Identify if response conditions are improving or worsening | CSZ
Critical Transportation | Situational Assessment | 2b | ESF 1 | Policy Group | Assist in the assessments of non-priority routes | CSZ
Mass Care Services | Operational Coordination | 2b | ESF 6 | ESF 5 | Integrate with external support operations that are participating in mass care operations: (1) Identify active external mass care participants to include in the SEOC ICS structure (to include the Private Sector) | CSZ
Mass Care Services | Operational Coordination | 2b | ESF 6 | ESF 11 | Assist and support local jurisdictions in coordinating safe, secure, and effective feeding and sheltering operations | CSZ
Mass Care Services | Operational Coordination | 2b | ESF 1 | ESF 6 | Prioritize assessment and repair resources which align with mass care operations and Priority Routes | CSZ
Mass Care Services | Operational Coordination | 2b | ESF 3 | ESF 6 | Identify government facilities that can be utilized for mass care activities | CSZ
Mass Care Services | Operational Coordination | 2b | ESF 4 | Planning Section | Identify personnel resources that can be utilized to fill local mass care operations (as appropriate and feasible) | CSZ
Mass Care Services | Operational Coordination | 2b | Operations Section | UCG | In coordination with ESF 5: (1) Request resource support from mutual aid and federal sources; (2) Ensure that meaningful reporting is occurring from local sources to aid in mass care support (i.e., EEI or Community Lifeline reporting) | CSZ
Mass Care Services | Operational Coordination | 2b | ESF 6 | Policy Group | In coordination with SEOC Logistics and ESF 7, identify and procure (if approved) resources to support local mass care operations | CSZ
Mass Care Services | Operational Coordination | 2b | ESF 11 | ESF 6 | In coordination with local and Tribal EOCs: (1) Identify feeding support available for local communities; (2) Provide nutrition assistance; (3) Ensure the safety of food supplies; (4) Provide for the safety and well-being of pets during emergency response operations and evacuations. | CSZ
Mass Care Services | Operational Coordination | 2b | ESF 13 | Policy Group | Identify resources available to protect mass care operations (as needed based on credible concerns) | CSZ
Mass Care Services | Operational Communications | 2b | ESF 2 | ESF 6 | Sustain communications ability with all mass care response partners | CSZ
Mass Care Services | Operational Communications | 2b | ESF 2 | ESF 6 | Sustain communications ability with all impacted jurisdiction’s mass care operations | CSZ
Mass Care Services | Operational Communications | 2b | ESF 2 | UCG | In coordination with ESF 6: (1) Identify communications solutions to address barriers with state, Tribal, and local mass care operations.; and (2) Identify available resources that can help support local jurisdiction’s mass care field operations | CSZ
Mass Care Services | Operational Communications | 2b | ESF 15 | JIC | Monitor for community-based communications concerning mass care | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2b | Logistics Section | ESF 7 | Integrate resources deployment for delivery of key supplies and response personnel alongside related activities | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2b | ESF 6 | UCG | Coordinate with appropriate agencies to determine bulk distribution needs of affected population | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2b | ESF 6 | Planning Section | Conduct ongoing assessment of mass care needs | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2b | ESF 6 | Planning Section | Sustain quantitative mass care services data to Planning and Logistics Sections, and other ESFs that require accurate data for response logistics | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2b | ESF 6 | ESF 11 | Re-evaluate system established for daily counting and reporting system for sheltering, feeding, and bulk distribution items delivered | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2b | ESF 1 | ESF 7 | Identify barriers and limitations in moving resources through transportation corridors which support mass care operations | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2b | ESF 7 | ESF 6 | In coordination with Logistics: (1) Identify state contracts for requested resources; (2) Identify resources for bulk purchases that support mass care; (3) Prepare to receive donations which are needed for bulk distribution; (4) Support local jurisdictions with coordination and delivery of water and shelf stable food to meet immediate needs (pre-CPOD deployment) | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2b | ESF 11 | ESF 6 | Identify needs to provide emergency supplies for pets and service animals: (1) Coordinate with agencies receiving donations for service and companion animals | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2b | ESF 12 | ESF 6 | In coordination with Logistics: (1) Identify fuel support for power generation at shelters and other mass care delivery sites; (2) Identify fuel support for evacuation operations | CSZ
Mass Care Services | Logistics and Supply Chain Management | 2b | ESF 15 | ESF 6 | Establish messaging for donations (wanted and unwanted) | CSZ
Mass Care Services | Situational Assessment | 2b | ESF 6 | UCG | Conduct ongoing assessment of mass care needs: (1) Analyze mass care operational reports for regional impacts and trends; (2) Share summary information with partners both vertically and horizontally; (3) Identify unmet needs; (4) Identify resource deficiencies in AFN support | CSZ
Mass Care Services | Situational Assessment | 2b | ESF 6 | Planning Section | Monitor on-going conditions of the Food, Water, Shelter & Health and Medical community lifelines: (1) Identify impacted areas where life safety or sustainment present significant challenges and require additional actions to occur | CSZ
Mass Care Services | Situational Assessment | 2b | ESF 6 |  | Sustain sheltering awareness through the WebEOC Shelter Status Dashboard | CSZ
Mass Care Services | Situational Assessment | 2b | ESF 6 | Planning Section | Sustain quantitative mass care services data for the Planning and Logistics Sections, and other ESFs that require accurate data for response logistics | CSZ
Mass Care Services | Situational Assessment | 2b | ESF 6 | ESF 11 | Sustain a daily counting and reporting system for sheltering, feeding, and bulk distribution items delivered: (1) Move to weekly reporting as appropriate | CSZ
Infrastructure Systems | Operational Coordination | 2b | Operations Section |  | In coordination with the SEOC Operations Section and the Business and Infrastructure Group, establish response objectives that reflect the coordination between infrastructure partners who share dependencies with impacted systems (water systems require fuel/electricity; transportation repairs may require water; fuel refinement requires potable water) | CSZ
Infrastructure Systems | Operational Coordination | 2b | Policy Group | Operations Section | In coordination with the Business and Infrastructure Group, Policy Group, and UCG, coordinate regulatory waivers and exemptions. | CSZ
Infrastructure Systems | Operational Coordination | 2b | ESF 1 |  | Assist local jurisdictions with accessing water infrastructure sites which have experienced damage to transportation access (to include aerial support) | CSZ
Infrastructure Systems | Operational Communications | 2b | ESF 2 |  | Coordinate with private sector providers to restore commercial voice and data communications capabilities in support of water infrastructure and water services | CSZ
Infrastructure Systems | Operational Communications | 2b | ESF 2 | ESF 15 | Assist local jurisdictions with communications capabilities to inform the public regarding the status of water systems, available resources, and public health notices (e.g., boil water advisories, etc.) | CSZ
Infrastructure Systems | Logistics and Supply Chain Management | 2b | Policy Group | Operations Section | In coordination with the Business and Infrastructure Group and UCG, consider waiving certification requirements for select personnel with expired(ing) credentials in order to address resource gaps or the inability to recertify | CSZ
Infrastructure Systems | Logistics and Supply Chain Management | 2b | ESF 6 | Logistics Section | Identify local CPODs and staging areas which require water resource support | CSZ
Infrastructure Systems | Logistics and Supply Chain Management | 2b | ESF 12 |  | Identify and coordinate fuel needs for water infrastructure (i.e., on-site generators) | CSZ
Infrastructure Systems | Logistics and Supply Chain Management | 2b | ESF 6 | Logistics Section | Procure, coordinate, and request additional water resources to support local needs (bottled water, RUPUs, water trailers, etc.) | CSZ
Infrastructure Systems | Logistics and Supply Chain Management | 2b | ESF 7 | ESF 8 | Identify state contracts that can utilized to support local water system repair or to supply water services over an extended timeframe | CSZ
Infrastructure Systems | Situational Assessment | 2b | ESF 8 | ESF 3 | Monitor and report the status of and damage to major water and wastewater providers covering large populations | CSZ
Infrastructure Systems | Situational Assessment | 2b | Logistics Section | ESF 12 | Monitor for portable generator requirements for sites providing water to impacted communities | CSZ
Infrastructure Systems | Situational Assessment | 2b | Operations Section | ESF 7 | In coordination with the Business and Infrastructure Group, identify supply chain deficiencies and shortfalls in supporting water infrastructure repair (based on local feedback of supply chain bottlenecks) | CSZ
Infrastructure Systems | Situational Assessment | 2b | ESF 11 |  | In coordination with ESF 11, identify water resource needed for agriculture and livestock | CSZ
All | Situational Assessment | 2a | ESF 5 | Planning Section | Provide information through appropriate state agencies, local partners, or the SEOC to inform response conditions (e.g., damage reports, 911 calls, Windshield Survey’s, Field Reports, and Witness Information). Information sources can include: Critical Infrastructure, Private Partners, VOADs, PSAPs, News Media. | CSZ
All | Situational Assessment | 2b | ESF 5 | Planning Section | Provide updated information through appropriate state agencies, local partners, or the SEOC to inform response conditions (e.g., damage reports, 911 calls, Windshield Survey’s, Field Reports, and Witness Information). Information sources can include: Critical Infrastructure, Private Partners, VOADs, PSAPs, News Media. | CSZ
All | Situational Assessment | 2a | Operations Section | ESF 5 | Provide local response information through the SEOC Representative | CSZ
All | Situational Assessment | 2b | Operations Section | ESF 5 | Provide updated local response information through the SEOC Representative | CSZ
All | Situational Assessment | 2a | Planning Section | ESF 5 | Identify local and Tribal Community Lifeline status and barriers or limitations for reestablishment | CSZ
All | Situational Assessment | 2b | Planning Section | ESF 5 | Sustain identification of local and Tribal Community Lifeline status and barriers or limitations for reestablishment | CSZ
All | Situational Assessment | 2a | ESF 5 | Planning Section | Establish local jurisdiction situation reporting to the SEOC | CSZ
All | Situational Assessment | 2b | ESF 5 | Planning Section | Sustain local jurisdiction situation reporting to the SEOC | CSZ
All | Situational Assessment | 2a | ESF 5 | Planning Section | Collect data from local jurisdictions and state agency partners | CSZ
All | Situational Assessment | 2b | ESF 5 | Planning Section | Sustain data collection from local jurisdictions and state agency partners | CSZ
All | Situational Assessment | 2a | Planning Section | UCG | Analyze data from local jurisdictions and interpret Community Lifeline status (if not already completed) | CSZ
All | Situational Assessment | 2b | Planning Section | UCG | Analyze data from local jurisdictions and interpret Community Lifeline status (if not already completed) | CSZ
All | Situational Assessment | 2a | Planning Section |  | Include Community Lifeline status and analysis in Situation Report | CSZ
All | Situational Assessment | 2b | Planning Section |  | Include Community Lifeline status and analysis in Situation Report | CSZ
All | Situational Assessment | 2a | Planning Section |  | Provide Community Lifeline analysis to the Geographic Information Unit. | CSZ
All | Situational Assessment | 2b | Planning Section |  | Provide Community Lifeline analysis to the Geographic Information Unit. | CSZ
All | Situational Assessment | 2a | Planning Section | SEOC Supervisor | Display data that is relevant for Community Lifeline statuses to aid in situational awareness and decision making | CSZ
All | Situational Assessment | 2b | Planning Section | SEOC Supervisor | Display data that is relevant for Community Lifeline statuses to aid in situational awareness and decision making | CSZ
All | Situational Assessment | 2a | Planning Section | SEOC Supervisor | Spotlight areas with significant disruption to Community Lifelines | CSZ
All | Situational Assessment | 2b | Planning Section | SEOC Supervisor | Spotlight areas with significant disruption to Community Lifelines | CSZ
All | Situational Assessment | 2a | Planning Section |  | Display HLS Regional damage and impact assessments | CSZ
All | Situational Assessment | 2b | Planning Section |  | Display HLS Regional damage and impact assessments | CSZ
All | Situational Assessment | 2a | Planning Section | Operations Section | Display significant resource deployments | CSZ
All | Situational Assessment | 2b | Planning Section | Operations Section | Display significant resource deployments | CSZ
All | Situational Assessment | 2a | Planning Section | SEOC Supervisor | Inquire about non-standard GIS needs | CSZ
All | Situational Assessment | 2b | Planning Section | SEOC Supervisor | Inquire about non-standard GIS needs | CSZ
All | Situational Assessment | 2a | Planning Section | SEOC Supervisor | Collation of information into the Community Lifeline Senior Leadership Briefs. | CSZ
All | Situational Assessment | 2b | Planning Section | SEOC Supervisor | Collation of information into the Community Lifeline Senior Leadership Briefs. | CSZ
All | Situational Assessment | 2a | Planning Section | UCG | Sharing and dissemination of information to local jurisdictions, state agency partners, federal partners, and the Unified Coordination Group and Policy Group | CSZ
All | Situational Assessment | 2b | Planning Section | UCG | Sharing and dissemination of information to local jurisdictions, state agency partners, federal partners, and the Unified Coordination Group and Policy Group | CSZ
All | Situational Assessment | 2a | ESF 15 | JIC | Translate Community Lifeline statuses and updates for public consumption | CSZ
All | Situational Assessment | 2b | ESF 15 | JIC | Translate Community Lifeline statuses and updates for public consumption | CSZ
All | Logistics and Supply Chain Management | 2a | Logistics Section |  | Activate any applicable memorandums of understanding (MOUs)/memorandums of agreement (MOAs) for chosen logistics sites | CSZ
All | Logistics and Supply Chain Management | 2a | Logistics Section |  | Initiate assessment of logistics sites | CSZ
All | Logistics and Supply Chain Management | 2a | Logistics Section | Planning Section | Establish and staff all logistics sites | CSZ
All | Logistics and Supply Chain Management | 2b | Logistics Section | UCG | Provide a joint expeditionary capability to rapidly assess, establish, repair, and operate SSAs within and outside the affected area | CSZ
All | Logistics and Supply Chain Management | 2b | Policy Group | UCG | In coordination with the UCG and the Policy Group establish objectives and priorities for resource allocation | CSZ
All | Logistics and Supply Chain Management | 2b | Logistics Section | Operations Section | In coordination with ESF 13 and ESF 20, determine need for and request security for movement and staging of resources | CSZ
All | Logistics and Supply Chain Management | 2b | ESF 7 | Logistics Section | Maintain coordination with the private sector to identify logistics shortfalls which the private sector can fill. | CSZ
All | Logistics and Supply Chain Management | 2b | Logistics Section |  | Staging Area managers continue to maintain food, water, dumpsters, hand-washing stations, portable toilets, and fuel distribution sites at ISBs, FSAs, and RSCs. | CSZ
All | Logistics and Supply Chain Management | 2b | Operations Section | Logistics Section | In coordination with ESF 1, ESF 6, ESF 7, ESF 11, and ESF 20, identify resource requirements and support the transportation resource requirements for the evacuation of people, service animals, and household pets. | CSZ
All | Operational Communications | 2a | ESF 2 |  | Identify communications requirements for internal and external stakeholders, local jurisdictions, and other response partners across the whole community. | CSZ
All | Operational Communications | 2b | ESF 2 |  | Reassess communications requirements for internal and external stakeholders, local jurisdictions, and other response partners across the whole community. | CSZ
All | Operational Communications | 2b | ESF 2 |  | Rebuild and/or reestablish EMD networks post-incident. | CSZ
All | Operational Communications | 2b | ESF 2 |  | Restore EMD system data from established backups. | CSZ
All | Operational Communications | 2a | ESF 2 |  | Restore communication for the SEOC with established or backup network providers. | CSZ
All | Operational Communications | 2a | ESF 2 | ESF 5 | Coordinate the assessment of local jurisdiction communication status. | CSZ
All | Operational Communications | 2b | ESF 2 | ESF 5 | Coordinate the reassessment of local jurisdiction communication status. | CSZ
All | Operational Communications | 2a | ESF 2 | ESF 5 | Deliver information on the current status of SEOC communication systems to local jurisdictions: (1) If direct communication to the local jurisdiction EOC is unavailable, assess the utilization of Public Safety Answering Points as a relay for communications. | CSZ
All | Operational Communications | 2b | ESF 2 | ESF 5 | Deliver information on the current status of SEOC communication systems to local jurisdictions: (1) If direct communication to the local jurisdiction EOC is unavailable, assess the utilization of Public Safety Answering Points as a relay for communications. | CSZ
All | Operational Communications | 2a | Logistics Section | ESF 2 | Provide communications capabilities for SEOC Representatives and other Field Forces. | CSZ
All | Operational Communications | 2b | Logistics Section | ESF 2 | Provide communications capabilities for SEOC Representatives and other Field Forces. | CSZ
All | Operational Communications | 2b | ESF 2 | Planning Section | Prepare communications demobilization and transition plan to ensure restoration efforts continue. | CSZ
All | Operational Communications | 2a | Operations Section | Logistics Section | If necessary, relay the status of the SEOC PACE communications status to the local, regional, or city PSAPs so interoperable communication can occur. | CSZ
All | Operational Communications | 2b | Operations Section | Logistics Section | If necessary, relay the status of the SEOC PACE communications status to the local, regional, or city PSAPs so interoperable communication can occur. | CSZ
All | Operational Communications | 2a | ESF 2 | Logistics Section | Setup and test portable network devices to provide communications between sections and ESF partners, policy group and elected officials. | CSZ
All | Operational Communications | 2b | ESF 2 | Logistics Section | Sustain network devices which provide communications between sections and ESF partners, policy group and elected officials. | CSZ
All | Operational Communications | 2a | ESF 2 | Logistics Section | Assess potential field personnel and facility communications requirements | CSZ
All | Operational Communications | 2b | ESF 2 | Logistics Section | Reassess potential field personnel and facility communications requirements | CSZ
All | Operational Communications | 2a | ESF 2 | Policy Group | Source mobile communications capability for isolated communities and other state identified priorities. | CSZ
All | Operational Communications | 2b | ESF 2 | Policy Group | Source mobile communications capability for isolated communities and other state identified priorities. | CSZ